## VDMSChange Request-Send to VMEP
Hanoi, 27 January 2010
| Thang Long Software Company |  | Ver 1.0
Address: 2/6-2/8 – Nui Thanh Street, 13 Ward, Tan Binh District, Ho Chi Minh City
VDMS Change Requirement
| To: | SYM
| Attn: | Mr. TSENG KUO CHOU
Thang Long software company would like to send our thankfulness to your support and trust in our services.
VDMS - Change Requirement |  |  |  | SD | SRS
No | FUNCTION NAME | Summary Content | OK/NG
1 | New Order Entry (update form) (Vehicle) | 1. The Bonus deductions: Add more fields allow dealer key-in the bonus data (get and check bonus data in Bonus Management module). They can keep these fields blank. These data should be apply when dealer modify order. | □ | 118
|  | 2. The Payment Data: Add fields allow dealer can key in the Payment data (as new order sheet form came from SALE) In case: Dealer have the payment data before make the order, dealer can key-in at this time. In case: Dealer do not have the payment keep blank |  | 120
2 | Bonus Query (new form) | 1. Bonus money tracking & query | □ | 109 | 55
3 | Sale man check & Confirm bonus (new form) | 1. Get Order data and confirm for bonus status only by sale man. | □ | 110 | 53
4 | Sale ADM process & Confirm Order at VDMS (update form) | 1. Sale ADM create order at Tip-Top site: | □
|  | Need Sale ADM choose 1 in the flowing case: * Manual case: Keep current order screen (cxmt411), Sale ADM key-in tiptop order manual * Auto Carrying Case: Change the tiptop order screen (cxmt411): add one more field in this screen, Sale ADM key-in VDMS order number, program should carry VDMS order data to tiptop (like VDMS-II). Sale ADM just check the order data in TIPTOP. If Sale ADM pass through the VDMS Order number (it’s null)  back to Manual Case |  | 119
2. Sale ADM confirm order at VDMS site
5 | Dealer key-in payment data (Order Edit function) Update form | Change the current Order Edit Screen: Allow dealer can modify the payment data and Bonus Data in orders has been send (not yet confirmed in tiptop side - VDMS must check) | □ | 120
6 | Payment Data Excel Upload | Each Bank has difference Excel file format (suggest that, system provide the parameters to define the excel file structure) HSBC, VCB, ACB, ANZ | □ | 114 | 56
7 | Check payment data before Re-Consign - Review payment data form (New form) | Create the preview screen before process the Re-consign. This screen summary the payment from Dealers, it has these columns: Dealer code Dealer Name Payment amount Payment Date Order Number Content, Bank Code, Transaction number. | □ | 115 | 57
8 | Do Auto Re-Consign form (New form) | When compare payment amount and Order Amount: Combine the Payment amount (From Banks) and Bonus Amount (from Bonus Management) Payment Amount = Bonus Amount (Dealer key-in on each order) + Bank Payment amount (From Bank’s data) 2. Query Re-Consign conditions Order Number Time range (From date …. To date) Dealer code Order Status (Payment confirmed or not) One Order has many payments  do total payment On doing re-consign: 1. If payment amount greater than Order Amount: Separate the payment amount to 2 parts: Equal to Order payment amount Remaining amount (may be used for next orders, has remark) The tiptop should used this data for module ANM. Allow tiptop get data has been confirm in VDMS side. 2. In case payment amount less than Order Amount: high-light the Orders and the allow VMEP’s FIN change the Payment data with these fields: Description and the TIPTOP voucher (more details in FIN confirm payment) | □ | 116 | 58
9 | Confirm Payment form - FIN (New form) | System provide the tool allow FIN can: confirm payment one-by-one. Confirm All Grouping by Dealer code and then list out these columns Order Number, Payment date, Payment Amount, Description, Tiptop Voucher number (Debit) Check selection, default value is: YES if payment amount equal to or greater than Order Amount. Otherwise NO. Confirm one button (by rows) Confirm All button | □ | 117 | 58
10 | Management Bonus Plan (Sale ADM) (New form) | Sale ADM define the bonus plan for each dealer in each month (Insert, Update, Delete, Report balance) | □ | 111 | 51
11 | Bonus Monthly Close (Sale ADM) (New form) | Sale ADM close bonus in each month to calculate bonus balance) | □ | 113 | 54
12 | Query Bonus (Sale ADM) (New form) | Sale ADM do query for bonus data reference | □
13 | Order Static Report (Sale ADM) (Sale ADM) (New form) |  | □
14 | Import/Sold-out Static Report (Sale ADM)(Sale ADM) (New form) |  | □
15 | Others | 1. System setting: Payment data Excel structure define 2. Update Order sheet layout (update payment info). | □
16 | Hide these function | a. Modify income data (Sale motorbike) b. Check needed receipts (Sale motorbike) c. Hide textbox: PRICE BEFORE TAX in sale screen | □
17 | New customer data (SRS screen) | Require field only: a. Full Name b. Phone Number or Mobile phone number | □

## PLAN
www.thanglongsoftware.net
VDMS CHANGE REQUEST PLAN 2010
SEQ | ITEM | From Date | To Date | Who | Remarks
I | Confirm Quotation
| Confirm quotation & contract | 28/01 | 04/02 | TLS & VMEP | 1 week
II | Update system & Go-Live
1 | Function program | 05/02 | 09/02 | TLS | 1 week
2 | Lunar New Year Holiday | 10/02 | 21/02 |  | 1.5 week
3 | Function program (continues) | 22/02 | 13/03 | TLS | 3 weeks
4 | Deploy to Test Server | 15/03 | 15/03 | TLS & VMEP
5 | VMEP IT Test (step 1) | 16/03 | 20/03 | IT VMEP | ~ 1 week
6 | TLS Fix program | 22/03 | 23/03 | TLS | 2 days
7 | VMEP IT Test (step 2) | 24/03 | 29/03 | IT VMEP | ~ 1 week
8 | Deploy into Production Server | 30/03 | 31/03 | TLS & VMEP | 2 days
9 | Go-live | 01/04 |  | VMEP
10 | TLS support and warranty | 01/04 |  | TLS